## Feuil1
CALLBOX: Scenario - This delivery is planned for version v 2.6.3
Changement |  |  | CHGT23525458 |  | Current Production Version | 2.6.3 | New Version | 3.0.4
CHGT23525458 :A5 (Reference Preprod change - )
Jira's/Incident |  |  | CAP-35635 CAP-35635 CAP-35635 CAP-35635 CAP-35635 CAP-35635
Times are FR / CET
3.0.4 delivery_CHGT23525458- 28th-JAUG-2024
Sr. No. | Start | Finish | Duration in Mins | Cutover Activity | Server | Owner | Follow up ownership | Start | End | Duration | Comments
| 15:00 |  | 120:00 | 28th-JAUG-2024
Prerequisite Before D-Day |  |  |  | Section Duration | 0:30
P-01 | 2024-07-15 | 2024-07-15 | 0:30 | Prepare SDI changement - CHGT23525458 | YVKS03R0 | PSA CAP | INDUS CAP
Deployment Procedure - 1 |  |  |  | Section Duration | 0:15
Pre-Requisite - 15TH JULY
P-01 | 14:00 | 15:00 | 2:00 | Version release | YVKS03R0 | PTA | INDUS CAP
P-02 | 15:00 | 15:15 | 0:15 | Data files for the version | YVKS03R0 | PTA | Indus CAP
Pre-Requisite - 28th Aug
P-01 | 15:00 | 15:15 | 0:15 | SDI change approval check | YVKS03R0 | Indus CAP | Indus CAP
P-02 | 15:15 | 15:16 | 0:01 | SVN Preparation | YVKS03R0 | Indus CAP | Indus CAP
P-03 | 15:16 | 15:46 | 0:30 | Applicative Package Preparation | YVKS03R0 | Indus CAP | Indus CAP
DEPLOYMENT - 1st Sept |  |  |  | SECTION DURATION | 2:42
"Application Deployment - YVKS03R0"
D-01 | 6:00 | 6:02 | 0:02 | Check the URL | http://mu.mes.callbox.inetpsa.com/ | Indus CAP | Indus CAP
D-02 | 6:02 | 6:07 | 0:05 | Get PGA approval before Stopping Monitoring | YVKS03R0 | Indus CAP | Indus CAP
D-03 | 6:07 | 6:12 | 0:05 | Stop application | YVKS03R0 | Indus CAP | Indus CAP
D-04 | 6:12 | 6:17 | 0:05 | Take the export of existing data | YVKS03R0 | Indus CAP | Indus CAP /PSA PGAs
D-05 | 6:17 | 6:27 | 0:10 | Drop Database | YVKS03R0 | Indus CAP | Indus CAP/PTA/PGA
D-06 | 6:27 | 6:32 | 0:05 | Install OSD | YVKS03R0 | Indus CAP | Indus CAP/PTA/PGA
D-07 | 6:32 | 7:02 | 0:30 | Run VMAJ scenario | YVKS03R0 | Indus CAP | Indus CAP/PTA/PGA
D-08 | 7:02 | 7:22 | 0:20 | Install Indusgen + update toolbox tbo06 | YVKS03R0 | Indus CAP | Indus CAP/PTA/PGA
D-09 | 7:02 | 7:32 | 0:30 | Create Database | YVKS03R0 | Indus CAP | Indus CAP/PTA/PGA
D-10 | 7:32 | 8:02 | 0:30 | DB import | YVKS03R0 | Indus CAP | Indus CAP/PTA/PGA
D-11 | 7:22 | 7:27 | 0:05 | Application start after the deployment + cron job activation + add config in ADM file | YVKS03R0 | Indus CAP | Indus CAP
D-13 | 7:27 | 7:37 | 0:10 | Verification of the application | YVKS03R0 | Indus CAP | Indus CAP/PTA/PGA
D-14 | 9:37 | 9:40 | 0:05 | ORACLE 19C Monitoring update in OSP + Reflex update + activate https url monitoring | YVKS03R1 | Indus CAP | Indus CAP/PTA/PGA
D-15 | 9:40 | 9:42 | 0:02 | OSP start | YVKS03R0 | Indus CAP | Indus CAP
Post-deployment Validation |  |  |  | Section Duration | 0:35
D-15 | 9:42 | 9:59 | 0:05 | Technical URL validation + Comparing Old and New datafiles | YVKS03R0 | Indus CAP/ PTA | Etudes
D-16 | 9:59 | 10:29 | 0:30 | Functional validation | YVKS03R0 | CAP DEV / PSA PGAs | CAP/ PSA PGAs
Rollback plan steps remains same, only database restore will be added
Rollback Plan |  |  |  | Section Duration | 1:22
Rollback of APPLICATION deployment = YVKS03R0 - Version2.6.3
R-01 | 10:29 | 10:31 | 0:02 | Stop Application | YVKS03R0 | Indus CAP | Indus CAP
R-02 | 10:31 | 10:36 | 0:05 | Take backup of new version deployed (data/j2ee/lib/sql) | YVKS03R0 | Indus CAP | Indus CAP
R-03 | 10:36 | 10:46 | 0:10 | Drop DB | YVKS03R0 | Indus CAP | Indus CAP
R-04 | 10:36 | 10:41 | 0:05 | Restore the backup of J2ee, lib, data & sql | YVKS03R0 | Indus CAP | Indus CAP
R-05 | 10:41 | 10:51 | 0:10 | Deploy the old War | YVKS03R0 | Indus CAP | Indus CAP
R-06 | 10:51 | 11:21 | 0:30 | Create Database | YVKS03R0 | Indus CAP | Indus CAP
R-07 | 10:51 | 11:06 | 0:15 | DB restore by importing dump taken before change using REPLACE option | YVKS03R0 | Indus CAP | Indus CAP
R-08 | 11:06 | 11:11 | 0:05 | Start the application | YVKS03R0 | Indus CAP | Indus CAP
R-09 | 11:11 | 12:16 | 1:05 | Remove HTTPS URL in monitoring as we as reflex + ora19c | YVKS03R0 | Indus CAP | Indus CAP
R-10 | 12:16 | 12:21 | 0:05 | Validation | YVKS03R0 | Indus CAP | Indus CAP

## Sheet2
Run Vmin scenario and Update JDK 1.8.0_321
Version Deployment and verification
Application start after the deployment
Verification of the application
OSP start

## Sheet1
Install the applicative tar present at $UNXAPPLI/Livarsion/P*/P*
Deployment verification
Execution of datbase queries and validation by PTA
Application start after the deployment
Verification of the application
OSP start

## Execution_Plan (hidden)
Sr No | Commands / Procedure | Duration | Comments | Server Name
#REF!
P-02 | http://atlantique.inetpsa.com/topaz/ | 0:15 | #REF! | YVKS03R0
#REF! | cd $UNXWEB cp resources resources_old | #REF! | Data files for the version | #REF!
#REF! | cd /users91/jbn00/web/AGA00.ear/ cp resources resources_old | #REF! | #REF! | #REF!
#REF!
#REF! | Run OSP_Disable_as_Custom_aga00 in Parallauncher | #REF! | #REF! | #REF!
#REF! | Run farmOut_as_custom_aga00 in Parallauncher | #REF! | #REF! | #REF!
Application Deployment - 1st Server = YVA2G10 - Version 6.4
D-02 | Run deployDevIndus_as_Custom_aga00 in Parallauncher | 0:05 | #REF! | YVKS03R0
D-03 | cd /users91/jbn00/web/AGA00.ear/ ls -l resources | 0:05 | Stop application | YVKS03R0
D-04 | Validation for Port 9080 | 0:05 | Take the export of existing data | YVKS03R0
#REF! | Validation for Port 9081 | #REF! | #REF! | #REF!
D-11 | Validation for Port 9082 | 0:05 | #REF! | YVKS03R0
#REF! | Validation for Port 9083 | #REF! | #REF! | #REF!
D-15 | Validation for Port 9084 | 0:02 | Application start after the deployment + cron job activation + add config in ADM file | YVKS03R0
Application Deployment - 2nd Server = YVA2G20 - Version 6.4
#REF! | Run deployDevIndus_as_Custom_aga00 in Parallauncher | #REF! | #REF! | #REF!
#REF! | cd /users91/jbn00/web/AGA00.ear/ ls -l resources | #REF! | #REF! | #REF!
#REF! | Validation for Port 9080 | #REF! | #REF! | #REF!
#REF! | Validation for Port 9081 | #REF! | #REF! | #REF!
#REF! | Validation for Port 9082 | #REF! | #REF! | #REF!
#REF! | Validation for Port 9083 | #REF! | #REF! | #REF!
#REF! | Validation for Port 9084 | #REF! | #REF! | #REF!
Application Deployment - 3rd Server = YVA2GM0 - Version 6.4
#REF! | Run deployDevIndus_as_Custom_aga00 in Parallauncher | #REF! | #REF! | #REF!
#REF! | cd /users91/jbn00/web/AGA00.ear/ ls -l resources | #REF! | #REF! | #REF!
#REF! | Validation for Port 9080 | #REF! | #REF! | #REF!
#REF! | Validation for Port 9081 | #REF! | #REF! | #REF!
#REF! | Validation for Port 9082 | #REF! | #REF! | #REF!
#REF! | Validation for Port 9083 | #REF! | #REF! | #REF!
#REF! | Validation for Port 9084 | #REF! | #REF! | #REF!
Application Deployment - 4th Server = YVA2GN0 - Version 6.4
#REF! | Run deployDevIndus_as_Custom_aga00 in Parallauncher | #REF! | #REF! | #REF!
#REF! | cd /users91/jbn00/web/AGA00.ear/ ls -l resources | #REF! | #REF! | #REF!
#REF! | Validation for Port 9080 | #REF! | #REF! | #REF!
#REF! | Validation for Port 9081 | #REF! | #REF! | #REF!
#REF! | Validation for Port 9082 | #REF! | #REF! | #REF!
#REF! | Validation for Port 9083 | #REF! | #REF! | #REF!
#REF! | Validation for Port 9084 | #REF! | #REF! | #REF!
Application Deployment -5th Server = YVA50V0 - Version 6.4
#REF! | $UNXEXSCRIPT/aga_stop.sh $UNXEXSCRIPT/aga_0EAR.sh | #REF! | #REF! | #REF!
#REF! | cd /users91/jbn00/web/AGA00.ear/ ls -l resources | #REF! | #REF! | #REF!
#REF! | ps -ef ¦grep -I http | #REF! | #REF! | #REF!
#REF! | $UNXEXSCRIPT/aga_start.sh | #REF! | #REF! | #REF!
#REF! | VALIDATION | #REF! | #REF! | #REF!
#REF! | VALIDATION | #REF! | #REF! | #REF!
#REF! | VALIDATION | #REF! | #REF! | #REF!
#REF!
#REF! | Run farmIn_as_custom_aga00 in Parallauncher | #REF! | #REF! | #REF!
#REF! | VALIDATION | #REF! | #REF! | #REF!
#REF! | VALIDATION | #REF! | #REF! | #REF!
Post-deployment Validation
D-15 | Validation | 1:00 | 1st Validation: Application must be validate(Check the functionality + Technical URL validation) + Monitor the Introscope => (Test AMOA, Test MOA) | YVKS03R0
D-16 | Validation | 1:00 | 2nd Validation: Application must be validate(Check the functionality + Technical URL validation) + Monitor the Introscope => (Test AMOA, Test MOA) | YVKS03R0
#REF! | Validation | 0:10 | Validate the FARM URL - from web security portal | #REF!
#REF! | Validation | 0:10 | Validate the Dynatrace for user frequency. | #REF!

## Rollback_Plan (hidden)
Sr No | Commands / Procedure | Duration | Comments | Server Name | Date
#REF!
#REF! | VALIDATION | #REF! | #REF! | #REF!
Rollback of APPLICATION deployment = YVKS03R0 - Version2.6.3
R-01 | Run deployDevIndus_as_Custom_aga00 in Parallauncher | 0:02 | Stop Application | YVKS03R0
R-02 | cd /users91/jbn00/web/AGA00.ear/ ls -l resources | 0:05 | Take backup of new version deployed (data/j2ee/lib/sql) | YVKS03R0
R-04 | Validation for Port 9080 | 0:05 | Restore the backup of J2ee, lib, data & sql | YVKS03R0
R-05 | Validation for Port 9081 | 0:10 | Deploy the old War | YVKS03R0
#REF! | Validation for Port 9082 | #REF! | #REF! | #REF!
R-08 | Validation for Port 9083 | 0:05 | Start the application | YVKS03R0
#REF! | Validation for Port 9084 | #REF! | #REF! | #REF!
#REF!
#REF! | Run deployDevIndus_as_Custom_aga00 in Parallauncher | #REF! | #REF! | #REF!
#REF! | cd /users91/jbn00/web/AGA00.ear/ ls -l resources | #REF! | #REF! | #REF!
#REF! | Validation for Port 9080 | #REF! | #REF! | #REF!
#REF! | Validation for Port 9081 | #REF! | #REF! | #REF!
#REF! | Validation for Port 9082 | #REF! | #REF! | #REF!
#REF! | Validation for Port 9083 | #REF! | #REF! | #REF!
#REF! | Validation for Port 9084 | #REF! | #REF! | #REF!
#REF!
#REF! | Run deployDevIndus_as_Custom_aga00 in Parallauncher | #REF! | #REF! | #REF!
#REF! | cd /users91/jbn00/web/AGA00.ear/ ls -l resources | #REF! | #REF! | #REF!
#REF! | Validation for Port 9080 | #REF! | #REF! | #REF!
#REF! | Validation for Port 9081 | #REF! | #REF! | #REF!
#REF! | Validation for Port 9082 | #REF! | #REF! | #REF!
#REF! | Validation for Port 9083 | #REF! | #REF! | #REF!
#REF! | Validation for Port 9084 | #REF! | #REF! | #REF!
#REF!
#REF! | $UNXEXSCRIPT/aga_stop.sh $UNXEXSCRIPT/aga_0EAR.sh | #REF! | #REF! | #REF!
#REF! | cd /users91/jbn00/web/AGA00.ear/ ls -l resources | #REF! | #REF! | #REF!
#REF! | ps -ef ¦grep -I http | #REF! | #REF! | #REF!
#REF! | $UNXEXSCRIPT/aga_start.sh | #REF! | #REF! | #REF!
#REF! | VALIDATION | #REF! | #REF! | #REF!
#REF! | VALIDATION | #REF! | #REF! | #REF!
#REF! | VALIDATION | #REF! | #REF! | #REF!
#REF!
#REF! | $UNXEXSCRIPT/aga_stop.sh $UNXEXSCRIPT/aga_0EAR.sh | #REF! | #REF! | #REF!
#REF! | cd /users91/jbn00/web/AGA00.ear/ ls -l resources | #REF! | #REF! | #REF!
#REF! | ps -ef ¦grep -I http | #REF! | #REF! | #REF!
#REF! | $UNXEXSCRIPT/aga_start.sh | #REF! | #REF! | #REF!
#REF! | VALIDATION | #REF! | #REF! | #REF!
#REF! | VALIDATION | #REF! | #REF! | #REF!
#REF! | VALIDATION | #REF! | #REF! | #REF!